## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… (itr1 = [Mon, Tues, Wed], itr2 = [Thu, Fri, Sat, Sun]
|  |  | Week 0 itr1 | Week 0 itr2 | Week 1 itr1 | Week 2 itr2 | Week 3 itr1 | Week 3 itr2
That User Story | Code Things…
Admin Create / Manage Employees | Admin functionality for Create employee ( login info and role) | 10 | 10 | 10 | 5 | 0 | 0 | 0
| Admin view for all employees (usernames, roles) | 8 | 6 | 2 | 0 | 0 | 0 | 0
| Admin ability to delete/ edit employees | 16 | 16 | 16 | 16 | 8 | 4 | 0
Admin/ Manger Group Management
| Functionality for All users view of all Groups Front/ Backend | 8 | 6 | 2 | 0 | 0 | 0 | 0
| Functionality for Admin/ Manger create Group Front/ Backend | 10 | 10 | 10 | 4 | 1 | 0 | 0
| Functionality for Admin/ Manger edit Group Front/ Backend | 10 | 10 | 10 | 10 | 10 | 5 | 0
| Functionality for Admin/ Manger remove Group Front/ Backend | 8 | 8 | 8 | 4 | 1 | 0 | 0
Admin/Manager create project | Manager functionality for create projects | 10 | 10 | 7 | 3 | 0 | 0 | 0
| Manager functionality for view/ edit/ delete projects | 20 | 10 | 2 | 2 | 2 | 2 | 2
| Manager functionality for assigning groups to projects | 6 | 6 | 6 | 6 | 4 | 2 | 0
| Manager functionality for removing groups from projects | 6 | 6 | 6 | 6 | 5 | 2 | 0
Admin/Manager edit project | Manager edit project's details (title) | 8 | 8 | 8 | 8 | 8 | 8 | 8
Base Login Page | User ability to use credentials to login | 6 | 2 | 0 | 0 | 0 | 0 | 0
|  | 126 | 108 | 87 | 64 | 39 | 23 | 10
Jeffrey
Stefan
Jacob