## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… (itr1 = [Mon, Tues, Wed], itr2 = [Thu, Fri, Sat, Sun]
|  |  | Week 0 itr1 | Week 0 itr2 | Week 1 itr1 | Week 1 itr2 | Week 2 itr1 | Week 3 itr2
That User Story | Code Things…
Admin Create / Manage Employees | Hash the password for created users | 10 | 10 | 5 | 0 | 0 | 0 | 0
| Remove DB id from user interface | 8 | 8 | 0 | 0 | 0 | 0 | 0
| Prevent admins from removing themselves | 8 | 8 | 0 | 0 | 0 | 0 | 0
| Prevent removal of employees who are referenced by a group or project | 10 | 10 | 10 | 10 | 10 | 0 | 0
| Admin functionality for editing employee | 14 | 10 | 10 | 10 | 10 | 0 | 0
Admin/ Manger Group Management | Managers can only edit their groups | 8 | 8 | 8 | 8 | 8 | 0 | 0
Admin/Manager Project Management | Managers can only edit their projects | 8 | 8 | 7 | 3 | 0 | 0 | 0
| Improve delete project functionality/UI | 10 | 10 | 2 | 2 | 2 | 0 | 0
| Manager functionality for editing projects | 14 | 14 | 0 | 0 | 0 | 0 | 0
| Add filtering for large lists | 8 | 8 | 8 | 8 | 8 | 0 | 0
| Manager functionality to aprove or reject joining a project | 20 | 6 | 6 | 6 | 5 | 0 | 0
Admin/Manager project boards | Managers functionality for viewing project boards for their projects | 20 | 20 | 16 | 16 | 16 | 0 | 0
| Managers functionality for viewing and editing kanban boards | 20 | 20 | 20 | 20 | 20 | 0 | 0
|  | 158 | 140 | 92 | 83 | 79 | 0 | 0
Jeffrey
Stefan
Jacob